## Summary
Value Bridge — status by phase, slice and function (2026-10-22)
Spec — none: only the one-line entry in the signed-off design, slice spec owed · drafted: written, not approved · approved: Ben approved it (or it was built from the signed-off design and his rulings).
Design — none: no slice design yet · drafted: schema written, not reviewed · reviewed: a design review is recorded for the slice · unknown: built, but no review is recorded.
Build — not started · partial: some of it works · built: complete on a branch, not merged · merged: on main.
Test (highest level reached) — none · unit: tests exist · full suite: covered by a recorded full test run · browser-checked: also seen working in a browser (ui-verifier or a recorded scripted check) · unknown.
Level | Name | Functions | Days left (10-20 plan) | Spec: none | Spec: drafted | Spec: approved | Spec: unknown | Design: none | Design: drafted | Design: reviewed | Design: unknown | Build: not started | Build: partial | Build: built | Build: merged | Test: none | Test: unit | Test: full suite | Test: browser-checked | Test: unknown
Phase | Built before the phase plan (on main) | 92 |  | 0 | 0 | 92 | 0 | 0 | 0 | 84 | 8 | 0 | 1 | 0 | 91 | 0 | 0 | 6 | 86 | 0
Slice | Slice 1 — Function chart, requirements, data, foundation | 22 |  | 0 | 0 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22 | 0
Slice | Slice 3 — DFD, ERD, Mermaid export | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Slice | Step retire | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 4a — Import pipeline (data entities and fields) | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
Slice | Slice 5 — Solutions | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
Slice | Slice 6a — Function requirements | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
Slice | Slice 6b-1 — Applications | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Slice | Slice 6b-2 — Interfaces | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 6c — Rate card and effort | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
Slice | Slice 7a — Project components, data model depth | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Slice | Slice 7b — Access: admin / user / viewer, restricted projects | 8 |  | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0
Slice | Slice 7c — The DFD rework (performers, triggers, as-is set) | 6 |  | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0
Slice | Slice 8 — Baseline freeze, approval, diff | 5 |  | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
Slice | Slice 10a — BR inside the chart; DFD screen | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 10b — BR ↔ FR direct | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0
Slice | Slice 10c — Organisation and Systems, BR attributes | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 10d — Ranked process panel, one RACI | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 11 — Structured BR, attributes used, system flows | 5 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
Slice | Slice 12 — Scope dashboard KPIs, project-management card | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0
Slice | Slice 13a — Solutions/FR split, readiness light | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
Slice | Slice 13b — DFD rule per chart | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Slice | Slice 13c — Process volume and FTE | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
Slice | Slice 13d — Draw connections on the DFD | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Slice | Slice 1g — Code list maintenance | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
Slice | Access slice A — Project admins | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0
Slice | Access slice B — Program members | 3 |  | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0
Phase | Phase 1 — Finish the scope core | 34 | 11.5 | 19 | 0 | 15 | 0 | 19 | 0 | 14 | 1 | 19 | 8 | 0 | 7 | 19 | 0 | 0 | 14 | 1
Slice | Slice 14 — Issue module | 7 | 0.5 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0
Slice | Control rules + control panel | 10 | 4 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
Slice | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 9 | 5 | 4 | 0 | 5 | 0 | 4 | 0 | 5 | 0 | 4 | 5 | 0 | 0 | 4 | 0 | 0 | 5 | 0
Slice | Slice 1f — Reports and PDF | 8 | 2 | 5 | 0 | 3 | 0 | 5 | 0 | 2 | 1 | 5 | 3 | 0 | 0 | 5 | 0 | 0 | 2 | 1
Phase | Phase 2 — Delivery control modules | 22 | 16 | 17 | 0 | 5 | 0 | 17 | 0 | 5 | 0 | 17 | 0 | 0 | 5 | 17 | 0 | 0 | 5 | 0
Slice | Slice 15 — Waves (phasing) | 5 | 2.5 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
Slice | Benefits | 4 | 2.5 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Slice | Change requests | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Slice | Risks | 4 | 2 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Slice | Decisions | 2 | 1.5 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Slice | WBS import + progress | 3 | 3.5 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Phase | Phase 3 — Ready for the first client | 14 | 15 | 2 | 0 | 12 | 0 | 2 | 0 | 12 | 0 | 8 | 1 | 5 | 0 | 8 | 0 | 5 | 1 | 0
Slice | Slice 16 — Archive files + project removal | 8 | 3.5 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 2 | 1 | 5 | 0 | 2 | 0 | 5 | 1 | 0
Slice | Slice 17 — Platform-admin grant approval | 4 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Slice | Client read-only login + offline viewer | 2 | 3 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Task (not a function) | Full review pass (Sara production depth; VB-005 backlog with Ben) |  | 2
Task (not a function) | Azure (Container Apps, private PostgreSQL, Key Vault, sign-in) |  | 4
Task (not a function) | Restore drill |  | 1
Task (not a function) | Prompt pack sign-off |  | 0.5
Phase | Phase 4 — After first client use | 4 | 9 | 3 | 0 | 1 | 0 | 3 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 1
Slice | Program roll-ups | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Slice | Languages | 1 | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Slice | Version comparison screen | 1 | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Phase | Unscheduled | 1 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Slice | No slice yet | 1 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
All |  | 167 | 51.5 | 42 | 0 | 125 | 0 | 42 | 0 | 115 | 10 | 48 | 11 | 5 | 103 | 48 | 0 | 11 | 106 | 2

## Functions
Phase | Slice | Days left (10-20 plan) | No | Function | ID | Spec | Design | Build | Test | Note | Slice evidence
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 1 | Add a business function | create_bfc_node | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 2 | Number the chart (01.02.03) | generate_bfc_code | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 3 | Reorder functions | reorder_bfc_node | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 4 | Mark / unmark a process | mark_process | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 5 | Describe a process | describe_process | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 10 | Link input / output data | link_bfc_data_entity | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 11 | Add an outside party | create_external_entity | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 12 | Link data exchanged with an outside party | link_bfc_external_flow | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 13 | As-is RACI on a process | link_bfc_role | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 16 | Organisation chart (units, roles) | maintain_org_chart | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 37 | Add a data entity | create_data_entity | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 38 | Manage data fields | manage_data_fields | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 42 | Business requirement created with a process | create_br | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 43 | Edit a business requirement | update_br | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 44 | Data a requirement uses (CRUD) | link_br_data_entity | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 85 | Sign in | login | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 89 | Add a client | create_client | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 90 | Create a project | create_project | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 98 | Retire a record (soft delete) | soft_delete_record | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 99 | Restore a retired record | restore_record | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 100 | Consistency check | consistency_check | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 1 — Function chart, requirements, data, foundation |  | 101 | Resolve code lists (company + project) | resolve_codes | approved | reviewed | merged | browser-checked |  | Signed-off design 09-28 (two review rounds) + slice 1 schema review 09-29; merged 52455cd; 115 tests on main; 12-step browser pass
Built before the phase plan (on main) | Slice 3 — DFD, ERD, Mermaid export |  | 23 | DFD to Mermaid text | export_dfd | approved | reviewed | merged | browser-checked |  | slice3_spec.md, review rounds 1–2; merged 6bed5d2/cc248d9/e56839b; 196 tests on main; ui-verifier per piece
Built before the phase plan (on main) | Slice 3 — DFD, ERD, Mermaid export |  | 32 | Save diagram positions | save_diagram_layout | approved | reviewed | merged | browser-checked |  | slice3_spec.md, review rounds 1–2; merged 6bed5d2/cc248d9/e56839b; 196 tests on main; ui-verifier per piece
Built before the phase plan (on main) | Slice 3 — DFD, ERD, Mermaid export |  | 40 | Generate the ERD | generate_erd | approved | reviewed | merged | browser-checked |  | slice3_spec.md, review rounds 1–2; merged 6bed5d2/cc248d9/e56839b; 196 tests on main; ui-verifier per piece
Built before the phase plan (on main) | Step retire |  | 15 | Retire / restore a process with what hangs off it | retire_step_with_dependents | approved | reviewed | merged | browser-checked |  | step_retire_spec.md, two review rounds; merged 955a0b3; 217 tests on main; ui-verifier 5/5
Built before the phase plan (on main) | Slice 4a — Import pipeline (data entities and fields) |  | 79 | 90-day purge of imported rows | purge_import_rows | approved | reviewed | merged | full suite | Built; no screen, so no browser check; the scheduled run on Azure comes with the Azure task | slice4a_spec.md + schema review 10-01; merged 7fcd815/8c08078/1c21198; 343 tests; browser 9/9 and 8/8 for 4a-1/4a-2, none recorded for the purge (4a-3)
Built before the phase plan (on main) | Slice 5 — Solutions |  | 47 | Link requirement to solution | link_br_solution | approved | reviewed | merged | browser-checked |  | slice5_spec.md, design review round 1; merged 364eb3f; 365 tests; ui-verifier 11/11
Built before the phase plan (on main) | Slice 5 — Solutions |  | 57 | Add a solution | create_solution | approved | reviewed | merged | browser-checked |  | slice5_spec.md, design review round 1; merged 364eb3f; 365 tests; ui-verifier 11/11
Built before the phase plan (on main) | Slice 6a — Function requirements |  | 58 | Add a function requirement | create_function_requirement | approved | reviewed | merged | browser-checked |  | slice6a_spec.md, review round 1 (1 high fixed); merged a8389d4; 383 tests; browser 12/12
Built before the phase plan (on main) | Slice 6a — Function requirements |  | 59 | Solution that carries an FR's effort | set_fr_solution | approved | reviewed | merged | browser-checked |  | slice6a_spec.md, review round 1 (1 high fixed); merged a8389d4; 383 tests; browser 12/12
Built before the phase plan (on main) | Slice 6b-1 — Applications |  | 14 | As-is systems behind a process | link_bfc_application | approved | reviewed | merged | browser-checked |  | slice6b1_spec.md, review round 1; merged fc91836; 402 tests; browser 12/12
Built before the phase plan (on main) | Slice 6b-1 — Applications |  | 62 | System catalogue | create_application | approved | reviewed | merged | browser-checked |  | slice6b1_spec.md, review round 1; merged fc91836; 402 tests; browser 12/12
Built before the phase plan (on main) | Slice 6b-1 — Applications |  | 63 | System that delivers a solution | link_application_solution | approved | reviewed | merged | browser-checked |  | slice6b1_spec.md, review round 1; merged fc91836; 402 tests; browser 12/12
Built before the phase plan (on main) | Slice 6b-2 — Interfaces |  | 60 | Interface detail | describe_interface | approved | reviewed | merged | browser-checked |  | slice6b2_spec.md, review round 1 (1 high fixed); merged 1107839; 425 tests; browser 12/12
Built before the phase plan (on main) | Slice 6c — Rate card and effort |  | 102 | Rate card | read_rate_card | approved | reviewed | merged | browser-checked |  | slice6c_spec.md, review round 1; merged 7c01033; 444 tests + deliberate-break check; browser 10/10
Built before the phase plan (on main) | Slice 6c — Rate card and effort |  | 103 | Adjust the rate card | maintain_rate_card | approved | reviewed | merged | browser-checked |  | slice6c_spec.md, review round 1; merged 7c01033; 444 tests + deliberate-break check; browser 10/10
Built before the phase plan (on main) | Slice 6c — Rate card and effort |  | 104 | Size an FR (effort days) | rate_function_requirement | approved | reviewed | merged | browser-checked |  | slice6c_spec.md, review round 1; merged 7c01033; 444 tests + deliberate-break check; browser 10/10
Built before the phase plan (on main) | Slice 6c — Rate card and effort |  | 105 | Effort summary | effort_summary | approved | reviewed | merged | browser-checked |  | slice6c_spec.md, review round 1; merged 7c01033; 444 tests + deliberate-break check; browser 10/10
Built before the phase plan (on main) | Slice 7a — Project components, data model depth |  | 39 | Data model warnings | validate_entity_model | approved | reviewed | merged | browser-checked |  | slice7_schema.md, review round 1 (13 findings, 7a–7c); merged b4be6bd; 460 tests; browser 8/8
Built before the phase plan (on main) | Slice 7a — Project components, data model depth |  | 91 | Project components on / off | set_components | approved | reviewed | merged | browser-checked |  | slice7_schema.md, review round 1 (13 findings, 7a–7c); merged b4be6bd; 460 tests; browser 8/8
Built before the phase plan (on main) | Slice 7a — Project components, data model depth |  | 92 | Data model depth | set_data_model_depth | approved | reviewed | merged | browser-checked |  | slice7_schema.md, review round 1 (13 findings, 7a–7c); merged b4be6bd; 460 tests; browser 8/8
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 86 | Add a user | create_user | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 87 | Change user type / platform admin | change_user_kind · set_platform_admin | approved | reviewed | merged | browser-checked | 87: slice 17 removes the direct grant (approval needed) | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 88 | Deactivate a user | deactivate_user | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 93 | Restrict a project | set_restriction | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 94 | Project members | manage_members | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 95 | Projects I can see | list_visible_projects | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 96 | Who can open this project | list_effective_access | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7b — Access: admin / user / viewer, restricted projects |  | 97 | Project access guard (404 → 403 → 409) | enforce_project_scope | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged f1dd75a; 465 tests; browser 8/9 then 6/6 recheck
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 17 | Copy a chart (as-is ⇄ to-be) | copy_bfc_set | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 18 | Who performs a process | set_performer | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 19 | Triggers list | maintain_process_trigger | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 20 | Trigger starts a process | link_process_trigger | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 21 | Generate the DFD | generate_dfd | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 7c — The DFD rework (performers, triggers, as-is set) |  | 24 | Process completeness check | process_completeness | approved | reviewed | merged | browser-checked |  | slice7_schema.md; merged 4f3ca3b; 462 tests; browser 7/10, 4 fixed; drag seen in slice 9
Built before the phase plan (on main) | Slice 8 — Baseline freeze, approval, diff |  | 80 | Freeze preview | preview_freeze | approved | reviewed | merged | browser-checked |  | slice8_schema.md, design-auditor 7 findings fixed; merged 01c8d1b; 499/499 tests; browser 9/10 + rechecks
Built before the phase plan (on main) | Slice 8 — Baseline freeze, approval, diff |  | 81 | Freeze a baseline | freeze_baseline | approved | reviewed | merged | browser-checked |  | slice8_schema.md, design-auditor 7 findings fixed; merged 01c8d1b; 499/499 tests; browser 9/10 + rechecks
Built before the phase plan (on main) | Slice 8 — Baseline freeze, approval, diff |  | 82 | Record client approval | approve_baseline | approved | reviewed | merged | browser-checked |  | slice8_schema.md, design-auditor 7 findings fixed; merged 01c8d1b; 499/499 tests; browser 9/10 + rechecks
Built before the phase plan (on main) | Slice 8 — Baseline freeze, approval, diff |  | 83 | Compare versions | diff_baseline | approved | reviewed | merged | browser-checked |  | slice8_schema.md, design-auditor 7 findings fixed; merged 01c8d1b; 499/499 tests; browser 9/10 + rechecks
Built before the phase plan (on main) | Slice 8 — Baseline freeze, approval, diff |  | 84 | Compare versions in person-days | priced_diff | approved | reviewed | merged | browser-checked |  | slice8_schema.md, design-auditor 7 findings fixed; merged 01c8d1b; 499/499 tests; browser 9/10 + rechecks
Built before the phase plan (on main) | Slice 10a — BR inside the chart; DFD screen |  | 22 | DFD list | dfd_index | approved | unknown | merged | browser-checked |  | D-53/D-54 ruled by Ben; no slice review recorded; merged f7bc276; 18 browser checks pass; no full run recorded for the slice itself
Built before the phase plan (on main) | Slice 10b — BR ↔ FR direct |  | 48 | Link requirement to FR directly | link_br_fr | approved | reviewed | merged | full suite |  | slice10b_spec.md, review round 1 (1 high); merged b7eb096; 530 tests; ui-verifier blocked twice — Ben tested the link himself
Built before the phase plan (on main) | Slice 10b — BR ↔ FR direct |  | 49 | Pick the FR's solution on the requirement | set_fr_solution_from_br | approved | reviewed | merged | full suite |  | slice10b_spec.md, review round 1 (1 high); merged b7eb096; 530 tests; ui-verifier blocked twice — Ben tested the link himself
Built before the phase plan (on main) | Slice 10b — BR ↔ FR direct |  | 50 | Create an FR from a requirement | create_fr_from_br | approved | reviewed | merged | full suite |  | slice10b_spec.md, review round 1 (1 high); merged b7eb096; 530 tests; ui-verifier blocked twice — Ben tested the link himself
Built before the phase plan (on main) | Slice 10c — Organisation and Systems, BR attributes |  | 45 | Fields a requirement's data holds | read_br_attributes | approved | reviewed | merged | browser-checked |  | slice10c_spec.md, review round 1 (1 high); merged bf89f32; 553 tests; browser 7/7
Built before the phase plan (on main) | Slice 10d — Ranked process panel, one RACI |  | 46 | To-be RACI on the requirement | link_br_role | approved | reviewed | merged | browser-checked |  | slice10d_spec.md, 11 findings (3 high) built in; merged bbd0674; 541 tests; ui-verifier 12 + recheck
Built before the phase plan (on main) | Slice 11 — Structured BR, attributes used, system flows |  | 51 | Requirement lines | maintain_br_lines | approved | unknown | merged | browser-checked |  | slice11_schema.md, rulings S11-1…S11-7; no design review recorded; merged 6c276c9; 663 tests on 772b93d; browser 10/10, 6/6, 6/6
Built before the phase plan (on main) | Slice 11 — Structured BR, attributes used, system flows |  | 52 | Fields a requirement uses (C/R/U) | tick_br_attributes | approved | unknown | merged | browser-checked |  | slice11_schema.md, rulings S11-1…S11-7; no design review recorded; merged 6c276c9; 663 tests on 772b93d; browser 10/10, 6/6, 6/6
Built before the phase plan (on main) | Slice 11 — Structured BR, attributes used, system flows |  | 53 | System-to-system flows | state_br_system_flow | approved | unknown | merged | browser-checked |  | slice11_schema.md, rulings S11-1…S11-7; no design review recorded; merged 6c276c9; 663 tests on 772b93d; browser 10/10, 6/6, 6/6
Built before the phase plan (on main) | Slice 11 — Structured BR, attributes used, system flows |  | 54 | Is each flow covered by an interface | flow_coverage | approved | unknown | merged | browser-checked |  | slice11_schema.md, rulings S11-1…S11-7; no design review recorded; merged 6c276c9; 663 tests on 772b93d; browser 10/10, 6/6, 6/6
Built before the phase plan (on main) | Slice 11 — Structured BR, attributes used, system flows |  | 55 | Create interface FRs from flows | create_interface_fr_from_flows | approved | unknown | merged | browser-checked |  | slice11_schema.md, rulings S11-1…S11-7; no design review recorded; merged 6c276c9; 663 tests on 772b93d; browser 10/10, 6/6, 6/6
Built before the phase plan (on main) | Slice 12 — Scope dashboard KPIs, project-management card |  | 141 | Scope dashboard (S1–S11) | scope_dashboard | approved | unknown | merged | full suite |  | slice12_kpis.md (S12-1); merged 7087ad4; no session record of its own — tests only through later full runs on main (821 at 5f3768e); browser check unknown
Built before the phase plan (on main) | Slice 12 — Scope dashboard KPIs, project-management card |  | 142 | Project-management card | pm_dashboard | approved | unknown | partial | full suite | M1 baselines and M3 issues built; M2 changes, M4 risks, M5 WBS come with their slices | slice12_kpis.md (S12-1); merged 7087ad4; no session record of its own — tests only through later full runs on main (821 at 5f3768e); browser check unknown
Built before the phase plan (on main) | Slice 13a — Solutions/FR split, readiness light |  | 25 | Readiness light per process | dfd_readiness | approved | reviewed | merged | browser-checked |  | slice13_spec.md (design review DR13); merged bd93239; 549 tests; ui-verifier run
Built before the phase plan (on main) | Slice 13b — DFD rule per chart |  | 26 | DFD rule | get_dfd_rule | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 8997dd5; 614 tests on main; browser check was Lilly's own scripted run, not ui-verifier
Built before the phase plan (on main) | Slice 13b — DFD rule per chart |  | 27 | Preview a DFD rule change | preview_dfd_rule | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 8997dd5; 614 tests on main; browser check was Lilly's own scripted run, not ui-verifier
Built before the phase plan (on main) | Slice 13b — DFD rule per chart |  | 28 | Set the DFD rule | set_dfd_rule | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 8997dd5; 614 tests on main; browser check was Lilly's own scripted run, not ui-verifier
Built before the phase plan (on main) | Slice 13c — Process volume and FTE |  | 6 | Process volume | set_process_volume | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged b4b8b6f; 614 tests at f174b4d; scripted browser 10/11 (11th the deliberate refusal)
Built before the phase plan (on main) | Slice 13c — Process volume and FTE |  | 7 | Hours and FTE worked out | derive_volume | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged b4b8b6f; 614 tests at f174b4d; scripted browser 10/11 (11th the deliberate refusal)
Built before the phase plan (on main) | Slice 13c — Process volume and FTE |  | 8 | FTE basis | set_fte_basis | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged b4b8b6f; 614 tests at f174b4d; scripted browser 10/11 (11th the deliberate refusal)
Built before the phase plan (on main) | Slice 13c — Process volume and FTE |  | 9 | Volume: as-is beside to-be | volume_summary | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged b4b8b6f; 614 tests at f174b4d; scripted browser 10/11 (11th the deliberate refusal)
Built before the phase plan (on main) | Slice 13d — Draw connections on the DFD |  | 29 | Draw a connection on the DFD | draw_dfd_connection | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 1a4e537; 563 tests; ui-verifier 6/7 + keyboard move
Built before the phase plan (on main) | Slice 13d — Draw connections on the DFD |  | 30 | Draw a hand-off between processes | draw_hand_off | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 1a4e537; 563 tests; ui-verifier 6/7 + keyboard move
Built before the phase plan (on main) | Slice 13d — Draw connections on the DFD |  | 31 | Remove a flow on the DFD | remove_dfd_flow | approved | reviewed | merged | browser-checked |  | slice13_spec.md; merged 1a4e537; 563 tests; ui-verifier 6/7 + keyboard move
Built before the phase plan (on main) | Slice 1g — Code list maintenance |  | 64 | FR types per project | maintain_fr_types | approved | reviewed | merged | browser-checked |  | slice1g_spec.md (G-1…G-6, design review); merged c930947; 746 tests on 1bb1e1a; browser 6/6
Built before the phase plan (on main) | Slice 1g — Code list maintenance |  | 144 | Code list maintenance | maintain_code_master | approved | reviewed | merged | browser-checked |  | slice1g_spec.md (G-1…G-6, design review); merged c930947; 746 tests on 1bb1e1a; browser 6/6
Built before the phase plan (on main) | Access slice A — Project admins |  | 151 | Project admins manage members (added) | appoint_project_admin | approved | reviewed | merged | browser-checked |  | slice_access_a_plan.md, access_v2_decision.md (design-auditor fixes §8); merged c930947; 700 → 746 tests; browser 5/7, both fails script errors
Built before the phase plan (on main) | Access slice A — Project admins |  | 152 | User-type change shows roles that come back (added) | user_type_change_preview | approved | reviewed | merged | browser-checked |  | slice_access_a_plan.md, access_v2_decision.md (design-auditor fixes §8); merged c930947; 700 → 746 tests; browser 5/7, both fails script errors
Built before the phase plan (on main) | Access slice B — Program members |  | 135 | Move a project to another program | move_project_program | approved | reviewed | merged | browser-checked |  | slice_access_b_plan.md; merged c930947; 746 tests on 3163a3c; browser 6/6
Built before the phase plan (on main) | Access slice B — Program members |  | 153 | Program members: admin / editor / viewer (added) | manage_program_members | approved | reviewed | merged | browser-checked |  | slice_access_b_plan.md; merged c930947; 746 tests on 3163a3c; browser 6/6
Built before the phase plan (on main) | Access slice B — Program members |  | 154 | Access list shows where each level comes from (added) | access_source | approved | reviewed | merged | browser-checked |  | slice_access_b_plan.md; merged c930947; 746 tests on 3163a3c; browser 6/6
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 69 | Stakeholders | create_stakeholder | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 70 | Raise an issue | raise_issue | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 71 | Link issue to requirements | link_issue_br | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 72 | Resolve / reopen an issue | resolve_issue | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 73 | Issue dashboard | issue_dashboard | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 155 | Edit / retire an issue (added) | edit_issue · retire_issue | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Slice 14 — Issue module | 0.5 | 156 | Issues frozen into baselines (added) | freeze_issues | approved | reviewed | merged | browser-checked |  | slice14_issue_spec.md (I-1…I-16), design review rounds 1–2; merged 8387fcb; 791 tests incl. slow; browser 9/10 + recheck on 10-20 — the 0.5 day in the plan is now spent
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 124 | Control rules | maintain_control_rule | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 125 | Control panel | control_panel | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 126 | Requirement volatility | requirement_volatility | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 127 | Where change lands | process_change_intensity | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 128 | Organisation impact | org_impact_heatmap | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 129 | Stakeholder engagement | stakeholder_engagement | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 130 | Interface load | interface_load | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 131 | Data migration map | data_migration_map | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 132 | Master data candidates | master_data_candidates | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Control rules + control panel | 4 | 133 | FRs with no requirement (threshold) | fr_unlinked | none | none | not started | none | Count already on the dashboard; threshold check not built | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 33 | Process-flow JSON schema and prompt pack | download_flow_schema | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 34 | Export process-flow JSON | export_process_flow_json | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 35 | Check a process-flow JSON import | validate_process_flow_json | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 36 | Commit a process-flow JSON import | commit_process_flow_json | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 74 | Excel template | download_template | approved | reviewed | partial | browser-checked | Built for data entities and fields (slice 4a, browser-checked); BR, FR, Issue here; WBS with the WBS slice | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 75 | Excel export | export_entity | approved | reviewed | partial | browser-checked | Built for data entities and fields (slice 4a, browser-checked); BR, FR, Issue here; WBS with the WBS slice | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 76 | Check an import | validate_import | approved | reviewed | partial | browser-checked | Built for data entities and fields (slice 4a, browser-checked); BR, FR, Issue here; WBS with the WBS slice | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 77 | Preview an import | preview_import | approved | reviewed | partial | browser-checked | Built for data entities and fields (slice 4a, browser-checked); BR, FR, Issue here; WBS with the WBS slice | Spec owed
Phase 1 — Finish the scope core | Slice 1e — Imports (BR, FR, Issue Excel; process-flow file) | 5 | 78 | Commit an import | commit_import | approved | reviewed | partial | browser-checked | Built for data entities and fields (slice 4a, browser-checked); BR, FR, Issue here; WBS with the WBS slice | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 41 | ERD export | export_erd | approved | reviewed | partial | browser-checked | Mermaid built (slice 3); PNG / SVG owed | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 56 | Requirements coverage report | br_coverage_report | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 61 | Interface list | interface_list | approved | reviewed | partial | browser-checked | Screen built (6b-2); Excel export owed | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 66 | Solution matrix | solution_matrix | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 67 | System gap report | application_gap_report | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 68 | Traceability matrix | fr_traceability_matrix | none | none | not started | none |  | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 134 | Add / edit a program | create_program · update_program | approved | unknown | partial | unknown | Add built; edit screen owed | Spec owed
Phase 1 — Finish the scope core | Slice 1f — Reports and PDF | 2 | 143 | Client reports to PDF | export_report_pdf | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Slice 15 — Waves (phasing) | 2.5 | 120 | Waves | create_phase | approved | reviewed | merged | browser-checked |  | slice15_phasing_spec.md (W-1…W-9), design review rounds 1–2; merged 5f3768e; 821 tests; browser 10/10 — the 2.5 days in the plan are now spent
Phase 2 — Delivery control modules | Slice 15 — Waves (phasing) | 2.5 | 121 | Split a solution across waves | assign_solution_phase | approved | reviewed | merged | browser-checked |  | slice15_phasing_spec.md (W-1…W-9), design review rounds 1–2; merged 5f3768e; 821 tests; browser 10/10 — the 2.5 days in the plan are now spent
Phase 2 — Delivery control modules | Slice 15 — Waves (phasing) | 2.5 | 122 | Solution dependencies | link_solution_dependency | approved | reviewed | merged | browser-checked |  | slice15_phasing_spec.md (W-1…W-9), design review rounds 1–2; merged 5f3768e; 821 tests; browser 10/10 — the 2.5 days in the plan are now spent
Phase 2 — Delivery control modules | Slice 15 — Waves (phasing) | 2.5 | 123 | Wave plan | phase_plan_report | approved | reviewed | merged | browser-checked |  | slice15_phasing_spec.md (W-1…W-9), design review rounds 1–2; merged 5f3768e; 821 tests; browser 10/10 — the 2.5 days in the plan are now spent
Phase 2 — Delivery control modules | Slice 15 — Waves (phasing) | 2.5 | 157 | Waves frozen into baselines (added) | freeze_waves | approved | reviewed | merged | browser-checked |  | slice15_phasing_spec.md (W-1…W-9), design review rounds 1–2; merged 5f3768e; 821 tests; browser 10/10 — the 2.5 days in the plan are now spent
Phase 2 — Delivery control modules | Benefits | 2.5 | 106 | Add a benefit | create_benefit | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Benefits | 2.5 | 107 | Link benefit to solution | link_benefit_solution | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Benefits | 2.5 | 108 | Value-for-effort ranking | value_ranking | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Benefits | 2.5 | 109 | No-benefit check | benefit_gap_report | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Change requests | 4 | 114 | Raise a change request | raise_change_request | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Change requests | 4 | 115 | Change impact trace | analyse_cr_impact | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Change requests | 4 | 116 | Price a change | price_cr | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Change requests | 4 | 117 | Decide a change | decide_cr | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Risks | 2 | 110 | Add a risk | raise_risk | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Risks | 2 | 111 | Score a risk | score_risk | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Risks | 2 | 112 | Risk becomes an issue | promote_risk_to_issue | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Risks | 2 | 113 | Risk register | risk_register | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Decisions | 1.5 | 118 | Record a decision | record_decision | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | Decisions | 1.5 | 119 | Decision log | decision_log | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | WBS import + progress | 3.5 | 138 | Link WBS lines | link_wbs_item | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | WBS import + progress | 3.5 | 139 | Record progress | record_wbs_progress | none | none | not started | none |  | Spec owed
Phase 2 — Delivery control modules | WBS import + progress | 3.5 | 140 | Progress report | wbs_progress_report | none | none | not started | none |  | Spec owed
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 149 | Archive file of each frozen baseline | export_baseline_archive | approved | reviewed | built | full suite | Written after each freeze; files owed are listed on the Removals tab | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 150 | Carry out an approved removal (operator) | purge_project | approved | reviewed | not started | none | Waits on migrations 0074 / 0075 (Ben's decision) | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 158 | Check an archive file reads back (added) | verify_archive_file | approved | reviewed | built | full suite |  | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 159 | Archive identity per database (added) | stamp_instance | approved | reviewed | built | full suite |  | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 160 | Removal request · approve · cancel; project locked while open (added) | removal_request | approved | reviewed | built | browser-checked | Ben tried it on 2026-10-21 | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 161 | Two-year clock and projects due for archiving (added) | archive_due_list | approved | reviewed | partial | full suite | Due list built; closing / reopening a project not started | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 162 | Request deletion of an archive (added) | delete_archive_request | approved | reviewed | built | full suite |  | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 16 — Archive files + project removal | 3.5 | 163 | Weekly archive check (added) | weekly_archive_check | approved | reviewed | not started | none |  | slice16_archive_purge_spec.md (AR-1…AR-13), review rounds 1–2 + one on the 10-18 changes; branch d36b56c, not merged; 904 tests on a596517; Removals tab ui-verifier 8/8
Phase 3 — Ready for the first client | Slice 17 — Platform-admin grant approval | 1 | 164 | Ask for someone to be made platform admin (added) | request_admin_grant | approved | reviewed | not started | none |  | slice17_admin_grant_spec.md + schema rev 2, AR-16…AR-23, review rounds 1–2; Ben's go 2026-10-21; build waits for Ben
Phase 3 — Ready for the first client | Slice 17 — Platform-admin grant approval | 1 | 165 | Approve / reject / cancel a request (added) | decide_admin_grant | approved | reviewed | not started | none |  | slice17_admin_grant_spec.md + schema rev 2, AR-16…AR-23, review rounds 1–2; Ben's go 2026-10-21; build waits for Ben
Phase 3 — Ready for the first client | Slice 17 — Platform-admin grant approval | 1 | 166 | Admin requests list (added) | list_admin_grants | approved | reviewed | not started | none |  | slice17_admin_grant_spec.md + schema rev 2, AR-16…AR-23, review rounds 1–2; Ben's go 2026-10-21; build waits for Ben
Phase 3 — Ready for the first client | Slice 17 — Platform-admin grant approval | 1 | 167 | Recorded grant by Fortience IS: first admins, fresh install (added) | owner_admin_grant | approved | reviewed | not started | none |  | slice17_admin_grant_spec.md + schema rev 2, AR-16…AR-23, review rounds 1–2; Ben's go 2026-10-21; build waits for Ben
Phase 3 — Ready for the first client | Client read-only login + offline viewer | 3 | 147 | Client read-only sign-in | client_readonly_login | none | none | not started | none |  | Spec owed
Phase 3 — Ready for the first client | Client read-only login + offline viewer | 3 | 148 | Offline viewer file | export_offline_viewer | none | none | not started | none |  | Spec owed
Phase 4 — After first client use | Program roll-ups | 2 | 136 | Program dashboard | program_dashboard | approved | unknown | partial | unknown | Member-project list built | Spec owed
Phase 4 — After first client use | Program roll-ups | 2 | 137 | Program roll-up figures | program_counts · interfaces · effort · control | none | none | not started | none |  | Spec owed
Phase 4 — After first client use | Languages | 4 | 145 | Language switch (EN / JA / TH) | switch_language | none | none | not started | none |  | Spec owed
Phase 4 — After first client use | Version comparison screen | 3 | 146 | Version comparison screen | version_compare_screen | none | none | not started | none | Comparison logic built (slice 8) | Spec owed
Unscheduled | No slice yet |  | 65 | Link an FR straight to a function | link_fr_to_bfc_node | none | none | not started | none |  | Designed, no date